## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | Module selection | As a TA applicant, I want to select up to three modules to apply for, So that I can apply for multiple opportunities while keeping my workload manageable. | Must have | version1.3 | * Students can select modules to apply for. * Maximum selection is limited to 3. | 3
2 | Selected number display | As a TA applicant, I want to see how many modules I have already selected, So that I can know whether I have reached the application limit. | Must have | version1.3 | * System is able to show the number of selected modules. * The system's counter updates in real time. * There is a warning when selected up to 3. | 2
3 | confirmation recieving | As a TA applicant, I want to receive confirmation after submitting my application, So that I know whether my application has been successfully recorded. | Must have | version1.3 | * Students can submit applications. * System can show configuration messages as a feedback. | 2
4 | page response speed | As a TA applicant, I want the system to load pages quickly, So that I do not waste time waiting when applying or reviewing applications. | Should have | version2.1 | * Pages load within reasonable time. | 2
5 | Private info protection | As a TA applicant, I want my personal information to be protected, So that only the MO and authorised people can view my info. | Should have | version2.1 | * Only authorised users can view personal data. * CV and personal info are protected. | 3
6 | Module info display | As a TA applicant, I want the system to display clear information about TA jobs, So that I can understand the requirements before applying for them. | Must have | version1.2 | * Students can see the basic info of modules. * The job list is displayed clearly. * Students can select a module and view its detailed informations. | 2
7 | Applicants viewing | As a Module organiser, I want to view a list of students who have applied for my module, So that I can easily evaluate the applicants who applied for my module. | Must have | version1.4 | * MO can see lists of applicants. * Each applicant show their name and ID. * The list is filtered by module. | 3
8 | CV viewing | As a Module organiser, I want to view each applicant's CV with one click, So that I can easily assess their experience and suitability without finding their name in a complicate folder. | Must have | version1.4 | * MO can click on a button to view CV. | 3
9 | Suitable candidate identification | As a Module organiser, I want to quickly identify suitable applicants, So that I don't have to spend a long time reviewing emails and documents. | Could have | version3.1 | * System can identify suitable candidates. | 5
10 | Application acceptance and rejection | As a Module organiser, I want to accept or reject applicants directly in the system, So that I can complete the recruitment process more efficiently. | Must have | version1.5 | * MO can click accept or reject button. * Status is updated immediately. | 3
11 | Simple interface | As a Module organiser, I want the interface to be simple and easy to use, So that I can understand how to use it without training. | Should have | version2.2 | * Interface is simple and clear. * Buttons are easy to find and understand. | 2
12 | Workload modification | As an Administrator, I want to monitor TA's workload more easily, So that I don't need to see each students' appliacation status. | Could have | version3.2 | * Admin can view TA workload. * Workload is calculated correctly. | 5
13 | Info display | As an Administrator, I want to view all posted TA jobs and applications, So that I can oversee the recruitment process. | Should have | version2.3 | * Admin can see all jobs. * Admin can see all of the applications. | 3
14 | Recruitment record display | As an Administrator, I want to view all TA recruitment records in one place, So that I can monitor the overall recruitment process. | Should have | version2.3 | * All recruitment records are stored. * Admin can view those records in one place. | 3
15 | Real time applicant number showing | As a TA applicant, I want to see real time numbers of applicants for each module. So that I can make a better decision. | Should have | version2.3 | * The system displays the number of applicants for each module. * The number is updated whenever a new application is submitted. | 3
16 | Module requirements posting | As a Module organiser, I want to post the TA recruitment basic information for my module, So that students can view the available TA requirements and apply for it. | Must have | version1.1 | * MO can enter module name, number of TA required, skills, working hours, start/end date. * All the fields must be filled before posting. * The job is saved and visible to students after posting. | 3